## Taul1
Work tracking sheet |  |  |  | Name: | Kihun Han
Signature:
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
27.11 | 14:00 | 16:10 |  | 2hr 10min | Make plan, check github, talk about User interface design
28.11 | 9:00 | 12:00 |  | 3hr | Try to figure out more and discuss about plan more
29.11 | 8:00 | 13:00 |  | 5hr | one was sick so can’t decide and discuss about wireframing so alone try to figure out javascript source code for math tools
30.11 | 9:00 | 14:00 |  | 5hr | change of plan, for UI design added one more day for partner while waiting partner to be done try to figure out about first function and get advice and help from teacher
1.12 | 13:00 | 14:00 |  | 1hr | Edit little about UI, wait partners answer, based on partner's design and work style suggested new plan and still discussion is going on
2.12 | 13:00 | 15:00 |  | 2hr | Studied math conception more about it permutation with replacement and without replacement
3.12 | 23:00 | 1:00 |  | 2hr | Check about function javascript
4.12 | 9:00 | 16:00 |  | 7hr | figure out second function(number system chart) and last function first try out and still figure out first one
5.12 | 9:00 | 15:00 |  | 6hr | make other functions basics and try to change first function(number conversion)
6.12 | 17:00 | 18:00 |  | 1hr | organize function one html file
7.12 | 9:00 | 14:00 |  | 5hr | Get advices about function A filtering better solution include method and try to start Html layout