## Taul1
Work tracking sheet |  |  |  | Name: | Kihun Han
kihun han
Signature:
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
27.11 | 14:00 | 16:10 |  | 2hr 10min | Make plan, check github, talk about User interface design
28.11 | 9:00 | 12:00 |  | 3hr | Try to figure out more and discuss about plan more
29.11 | 8:00 | 13:00 |  | 5hr | one was sick so can’t decide and discuss about wireframing so alone try to figure out javascript source code for math tools
30.11 | 9:00 | 14:00 |  | 5hr | change of plan, for UI design added one more day for partner while waiting partner to be done try to figure out about first function and get advice and help from teacher
1.12 | 13:00 | 14:00 |  | 1hr | Edit little about UI, wait partners answer, based on partner's design and work style suggested new plan and still discussion is going on
2.12 | 13:00 | 15:00 |  | 2hr | Studied math conception more about it permutation with replacement and without replacement
3.12 | 23:00 | 1:00 |  | 2hr | Check about function javascript
4.12 | 9:00 | 16:00 |  | 7hr | figure out second function(number system chart) and last function first try out and still figure out first one
5.12 | 9:00 | 15:00 |  | 6hr | make other functions basics and try to change first function(number conversion)
6.12 | 17:00 | 18:00 |  | 1hr | organize function one html file
7.12 | 9:00 | 14:00 |  | 5hr | Get advices about function A filtering better solution include method and try to start Html layout
8.12 | 9:00 | 15:00 |  | 6hr | After setting up basic layout then try to insert function in every pages until so far function 2 is inserted
9.12 | 19:00 | 21:00 |  | 2hr | adding global navigation as famous website's logo and trim little about number chart function
10.12 | 22:00 | 24:00 |  | 2hr | finding out error in random values function so try to fix it
11.12 | 9:00 | 16:00 |  | 7hr | implementation for project html file from function javascript and try to figure out function c ( truth table) more
12.12 | 9:00 | 13:00 |  | 4hr | implementation for function c (truth table)
13.12 | 11:00 | 15:30 |  | 4hr 30min | puttig html layout more and made combinatorics differently and random value make sort